## Week 1
Reported hours for:
Activity	Time (hours)
E-mail with client	1
Group contract	5
project plan	1
meetings (external & internal)	4,5
Prepare for meetings	1

## Week 2
Reported hours for:
Activity	Time (hours)
Updating GIT and Trello	1
Meetings (internal)	5
meeting (external)	0,4
project plan (writing text)	7
Prepare for meetings	1
E-mail with client	1
Other/helping out	1

## Week 3
Reported hours for:
Activity	Time (hours)
Updating GIT and Trello	1
Meetings (internal)	4
meeting (external)	0,5
Design description	1
Prepare for meetings	1
E-mail with client	1
Other/helping out	1
Meeting (client)	1
Presentation preparation	2,5
Presentation (real)

## Week 4
Reported hours for:
Activity	Time (hours)
internal meeting	2
external meeting	1
design description	10
client meeting	0.5
steering meeting notes	0.5

## Week 5
Reported hours for:
Activity	Time (hours)
internal meeting	5
external meeting	1
design description fixes	3
design presentation ppt	3
Meeting with client	1
Trello/GIT/slack	3

## Week 6
Reported hours for:
Activity	Time (hours)

## Week 7
Reported hours for:
Activity	Time (hours)

## Week 8
Reported hours for:
Activity	Time (hours)

## Week 9
Reported hours for:
Activity	Time (hours)

## Week 10
Reported hours for:
Activity	Time (hours)