## Backlog
Id | Priority | Sprint | Userstory | User | Goal/Aim | Reason/Why | Acceptance | Short description | Comment
1 | 50 | 1 | As user I want to see the highscore so that I can compare it to other people. | user | see the highscore | I can compare it to other people | A button to see the highscore. | Highscore
Note on B1: Autor: Priorities from 0 to 100 (100 is very important)
Note on D1: Autor: filled automatically

## Sprint 1
| Story-Id | Story | Acceptance
| 1 | As user I want to see the highscore so that I can compare it to other people. | A button to see the highscore.
| 2 | #N/A | #N/A
| 3 | #N/A | #N/A
Backlog-Id | Task-Id | Story-description | Task | Status | estimated Value/hours | estimated rest effort | previous effort | Responsible Person | Comment
1 | 1.1.1 | Highscore | design in GUI-Builder | done | 1 | 0 | 0.5 | Hans
1 | 1.1.2 | Highscore | save score | todo | 8 | 8 | 0 | Peter und Jakob
1 | 1.1.3 | Highscore | restore the score | todo | 8 | 8 | 0 | Peter
1 | 1.1.4 | Highscore | connect data and GUI | todo | 4 | 4 | 0 | Peter
Note on B7: Autor: <SprintNr>.<Backlog-Id>.<TaskNr>