## Week_1
Reported hours for: Charlie Höglund
Activity	Time (hours)
project plan	1.5
meetings (internal & external)	4.5
learning trello & github	2

## Week_2
Reported hours for: Charlie Höglund
Activity	Time (hours)
monday's project meeting slides (e.g. powerpoint, updating the trello board)	1
meetings (internal & external - client meeting included)	4.5
project plan (writing text, checking related course documents, client's excel files etc.)	13
learning github (e.g. downloading and using github desktop)	1

## Week_3
Reported hours for: Charlie Höglund
Activity	Time (hours)
client meeting	1
internal & external meeting	4.5
project plan & requirements presentation slides	4.5
presentation & watching other presentations	2.5
slides for steering goup meeting, updating trello	1.5

## Week_4
Reported hours for: Charlie Höglund
Activity	Time (hours)
preparation for steering group meeting (ppt slides, update trello)	2
internal meeting	0.5
external meeting	0.5
design description	13
client meeting	0.5
client meeting notes	0.5
project plan	1

## Week_5
Reported hours for:
Activity	Time (hours)
external meeting	0.5
steering group slides & update trello	1
internal meeting	3
presentation slides (design & implementation)	9
presentation & watching presentations	2.5
implementation - cash flow diagram columns	2

## Week_6
Reported hours for:
Activity	Time (hours)
presentation slides/update trello (Monday)	2
steering group meeting	0.5
internal meeting	3.5
other (client questions, setup things etc)	1.5
external meeting (client meeting included)	1
implementation & testing	5.5

## Week_7
Reported hours for:
Activity	Time (hours)
steering group slides & report	3
implementation & testing	7.5
internal meeting	2.5
client contact	0.5

## Week_8
Reported hours for:
Activity	Time (hours)
final project report	0.5
internal communication	0.5

## Week_9
Reported hours for:
Activity	Time (hours)
internal meeting	4.5
implementation	1
final report	5.5
final presentation	0.5

## Week_10
Reported hours for:
Activity	Time (hours)